# NeoBank Retail Banking Portal

Comprehensive 2-Week Agile Sprint Plan (Frontend & Backend Jira Epics, Stories, and Detailed Technical Tasks)

Table of Contents

1. Executive Summary & 2-Week Sprint Strategy

2. JIRA Epic Hierarchy & Coverage Mapping

3. Sprint 1 Backlog: Foundation, Accounts, Security & Admin (Days 1–7)

EPIC-01: Security, Authentication & Session Inactivity (BNK-FR-07)

EPIC-02: Customer Account Management & Transaction Ingestion (BNK-FR-01)

EPIC-03: Beneficiary Onboarding & Activation Management (BNK-FR-02)

EPIC-04: Account Statement Generation & Export (BNK-FR-05)

EPIC-05: Branch Admin Account & Loan Approval Workflow (BNK-FR-08)

4. Sprint 2 Backlog: Simulated Transfers, Schedules, Loans & AI (Days 8–14)

EPIC-06: Simulated Fund Transfers (Own, Other Bank, Mock UPI) (BNK-FR-03)

EPIC-07: Scheduled & Recurring Transfer Engine (BNK-FR-04)

EPIC-08: Loan Application, Eligibility & EMI Calculator (BNK-FR-06)

EPIC-09: Simulated AI Insights & Risk Assessment (BNK-AI-01 to 05)

5. Comprehensive Task Master Reference (For Jira Import)

# 1. Executive Summary & 2-Week Sprint Strategy

This document establishes the ready-to-copy JIRA Backlog structure (Epics, User Stories, and granular Frontend/Backend Sub-tasks) for the NeoBank Retail Internet Banking Portal, derived directly from the approved Product Requirements Document (PRD v1.0). The engineering delivery is structured across two 7-day sprints covering complete end-to-end functionality across Customer, Teller, Loan Officer, and Branch Admin roles.

CRITICAL PRODUCT CONSTRAINT: In strict accordance with the approved PRD, all monetary transactions and fund movements within NeoBank are completely SIMULATED. The system simulates transactional lifecycles, ledger updates, OTP verification, mock UPI responses, and mock external bank routing without integrating real-world payment rails.

| Sprint | Focus & Core Modules | Frontend Deliverables | Backend Deliverables | Story Points Target |
| --- | --- | --- | --- | --- |
| Sprint 1 (Days 1–7) | Foundation, Security, Accounts, Beneficiaries, Statements & Admin Workflows | Auth & Virtual Keyboard, Inactivity Timer, Accounts Dashboard, Beneficiary Form & Activation, Statement Generator UI, Branch Admin Approval Queue UI | JWT Auth & Session Management, Account & Transaction REST APIs, Beneficiary Lifecycle Engine, Statement PDF Renderer, Branch Admin KYC/Account Approval Service | 65 Story Points |
| Sprint 2 (Days 8–14) | Simulated Transfers, Schedules, Loans & AI Enhancements | Own Account / Other Bank / Mock UPI Transfer Wizards, Scheduled/Recurring Transfer Manager, Loan Application & EMI Calculator, Risk & KYC AI Badges | Simulated Fund Transfer Engine (Atomicity & Locks), Cron Scheduler for Recurring Rules, Loan Processing Engine, Rule-Based AI Risk & Categorization Endpoints | 70 Story Points |

Table 1: 2-Week Sprint Execution Framework (Frontend & Backend Breakdown)

# 2. JIRA Epic Hierarchy & Coverage Mapping

| Epic Key | Epic Name | PRD Feature Ref | Sprint | Primary Roles |
| --- | --- | --- | --- | --- |
| EPIC-01 | Security, Authentication & Session Inactivity | BNK-FR-07 | Sprint 1 | Customer, Branch Admin |
| EPIC-02 | Customer Account Management & Transaction Ingestion | BNK-FR-01 | Sprint 1 | Customer |
| EPIC-03 | Beneficiary Onboarding & Activation Management | BNK-FR-02 | Sprint 1 | Customer |
| EPIC-04 | Account Statement Generation & Export | BNK-FR-05 | Sprint 1 | Customer |
| EPIC-05 | Branch Admin Account & Loan Approval Workflow | BNK-FR-08 | Sprint 1 | Branch Admin |
| EPIC-06 | Simulated Fund Transfers (Own, Other Bank, Mock UPI) | BNK-FR-03 | Sprint 2 | Customer |
| EPIC-07 | Scheduled & Recurring Transfer Engine | BNK-FR-04 | Sprint 2 | Customer |
| EPIC-08 | Loan Application, Eligibility & EMI Calculator | BNK-FR-06 | Sprint 2 | Customer, Loan Officer |
| EPIC-09 | Simulated AI Insights & Risk Assessment | BNK-AI-01 to 05 | Sprint 2 | Customer, Branch Admin |

Table 2: JIRA Epic Mapping against PRD Modules

# 3. Sprint 1 Backlog: Foundation, Accounts, Security & Admin (Days 1–7)

## EPIC-01: Security, Authentication & Session Inactivity (BNK-FR-07)

Epic Description: Implement banking-grade authentication, virtual scrambled keyboard for password input, 5-minute inactivity session tracking with popup warnings, and secure logout across roles.

### Story 1.1: Virtual Keyboard & Secure Customer Login

User Story: As a NeoBank customer, I want to authenticate using credentials with an optional randomized virtual keyboard so that my password is safe from keyloggers.

Acceptance Criteria:
• Virtual keyboard can be toggled on/off on the password field.
• Keyboard layout randomizes keys upon display.
• Supports PIN/alphanumeric characters, backspace, and clear.
• Masked password input with eye toggle.
• Failed login attempts trigger appropriate error messaging without leaking user existence.

Sub-Tasks Breakdown:

- TASK-01-FE-01: Build accessible, scrambled Virtual Keyboard React/Angular component with key click event masking.

- TASK-01-FE-02: Create Login page UI with form validation, eye password toggle, and error banner handling.

- TASK-01-BE-01: Implement Spring Security JWT authentication endpoints with BCrypt password hashing.

- TASK-01-BE-02: Configure Rate Limiting (Bucket4j / Redis) and failed login lockout mechanisms.

### Story 1.2: Session Inactivity Timer & Warning Dialog

User Story: As an authenticated user, I want a warning after 5 minutes of inactivity so that I can extend my session before being automatically logged out.

Acceptance Criteria:
• Activity listeners track mouse movement, keyboard events, clicks, and touches.
• At 5 minutes of total idle time, display a modal dialog with a 60-second countdown.
• Clicking 'Stay Logged In' refreshes the session token silently.
• If countdown reaches zero, invalidate token, clear client storage, and redirect to login with timeout notice.

Sub-Tasks Breakdown:

- TASK-01-FE-03: Implement global Inactivity Timer hook/service tracking DOM activity events.

- TASK-01-FE-04: Create Timeout Warning Modal with 60-second real-time countdown progress bar.

- TASK-01-BE-03: Implement Token Refresh endpoint (`/api/v1/auth/refresh`) and Server-Side Session Invalidation.

- TASK-01-BE-04: Add audit log event capture for session timeouts and manual logouts.

## EPIC-02: Customer Account Management & Transaction Ingestion (BNK-FR-01)

Epic Description: Provide customers with full visibility into their savings/checking accounts, available balances, recent transaction history, filtering, and simulated mock feeds.

### Story 2.1: Account Summary & Overview Dashboard

User Story: As an authenticated customer, I want to view all my active accounts, balances, and quick actions upon logging into the dashboard.

Acceptance Criteria:
• Display total net balance, savings account card, and current account card.
• Show masked account numbers with copy-to-clipboard functionality.
• Account cards show currency, available balance, status (Active/Frozen), and quick action buttons (Transfer, Statement).

Sub-Tasks Breakdown:

- TASK-02-FE-01: Create responsive Account Summary card widgets with balance toggle (hide/show balance).

- TASK-02-FE-02: Implement Dashboard Layout with Quick Action shortcuts and account switching tabs.

- TASK-02-BE-01: Develop Account Query Service & REST Controller (`GET /api/v1/accounts/summary`).

- TASK-02-BE-02: Write Flyway migrations for accounts schema (`customer_accounts`, `account_types`, `account_status`).

### Story 2.2: Transaction History & Filterable Ledger

User Story: As a customer, I want to browse, search, and filter my recent transactions by date, amount, type, and status so that I can monitor my financial activity.

Acceptance Criteria:
• Paginated transaction table with sorting by date, debit/credit color indicators, and reference numbers.
• Filter by date range (Today, Last 7 Days, Last Month, Custom), transaction type (Credit/Debit), and search keyword.
• Clicking a row opens a transaction details drawer/modal with simulated reference IDs.

Sub-Tasks Breakdown:

- TASK-02-FE-03: Build Paginated Transaction Data Grid with search filters and expandable detail modal.

- TASK-02-FE-04: Implement Transaction Category badges and Debit/Credit visual styling.

- TASK-02-BE-03: Create Paginated Transaction Search API (`GET /api/v1/accounts/{id}/transactions`) with Spring Data Specifications.

- TASK-02-BE-04: Seed realistic simulated transaction dataset via Flyway/Liquibase migration for testing.

## EPIC-03: Beneficiary Onboarding & Activation Management (BNK-FR-02)

Epic Description: Allow customers to add new beneficiaries for intra-bank, inter-bank (IFSC/SWIFT), and Mock UPI, with pending lifecycle states and simulated activation cooldowns.

### Story 3.1: Add Beneficiary Form & Multi-Rail Validation

User Story: As a customer, I want to add new beneficiaries with account details or UPI VPA so that I can initiate transfers to them.

Acceptance Criteria:
• Form supports 3 beneficiary types: Same Bank (NeoBank), Other Bank (IFSC/Account No), and Mock UPI.
• Real-time client-side and server-side validation: Account number confirmation matching, IFSC format validation (4 letters + 0 + 6 alphanumeric), and UPI ID regex (`user@mockbank`).
• Beneficiary nickname and maximum transfer limit configuration.

Sub-Tasks Breakdown:

- TASK-03-FE-01: Create Multi-Tab Add Beneficiary wizard with dynamic field validation rules.

- TASK-03-FE-02: Implement IFSC Bank/Branch mock lookup auto-filler component.

- TASK-03-BE-01: Develop Beneficiary Management Service & REST APIs (`POST /api/v1/beneficiaries`).

- TASK-03-BE-02: Implement IFSC and UPI VPA validation logic and duplicate beneficiary prevention checks.

### Story 3.2: Beneficiary Activation & Cooling-Off Period Workflow

User Story: As a customer, I want to verify beneficiary creation via OTP and see their activation status so that I know when they are eligible for transfers.

Acceptance Criteria:
• Submission triggers simulated OTP modal.
• Upon valid OTP, beneficiary enters 'Active' (or 30-minute cooling period state based on bank rule).
• Beneficiary listing page displays Active, Pending, and Inactive filters with delete/edit actions.

Sub-Tasks Breakdown:

- TASK-03-FE-03: Build Beneficiary List view with status badges, cooling-off countdown timer, and manage actions.

- TASK-03-FE-04: Implement OTP Verification Dialog with resend countdown timer.

- TASK-03-BE-03: Implement Simulated OTP Generation and Verification Service (`POST /api/v1/otp/verify`).

- TASK-03-BE-04: Create Beneficiary Activation Lifecycle Manager and Cooling-Off scheduler.

## EPIC-04: Account Statement Generation & Export (BNK-FR-05)

Epic Description: Allow customers to generate, view online, and download historical account statements in PDF/CSV format with date range customization.

### Story 4.1: Statement Customization & On-Screen Viewer

User Story: As a customer, I want to choose a date range or fiscal quarter to view my account statement on screen.

Acceptance Criteria:
• Account selector, date presets (Last 1 Month, Last 3 Months, Last 6 Months, Current FY, Custom Date Range).
• Summary view displaying opening balance, total debits, total credits, and closing balance.

Sub-Tasks Breakdown:

- TASK-04-FE-01: Build Statement Generator UI form with date pickers and balance summary cards.

- TASK-04-FE-02: Create responsive on-screen Statement Preview component with print styles.

- TASK-04-BE-01: Implement Statement Query & Calculation Service (`GET /api/v1/statements/preview`).

### Story 4.2: Statement PDF & CSV Download Service

User Story: As a customer, I want to download my statement as a formatted PDF or CSV file for my records.

Acceptance Criteria:
• Download PDF button generates formatted document containing bank header, customer details, simulated watermark, and statement ledger.
• Download CSV generates clean tabular raw data for spreadsheet analysis.

Sub-Tasks Breakdown:

- TASK-04-FE-03: Implement PDF/CSV direct blob download triggers with loading indicators.

- TASK-04-BE-02: Build high-performance PDF Generator using OpenPDF/iText/Thymeleaf with simulated bank branding.

- TASK-04-BE-03: Implement streaming CSV exporter for large transaction date ranges.

## EPIC-05: Branch Admin Account & Loan Approval Workflow (BNK-FR-08)

Epic Description: Provide branch administrators and officers with role-based back-office dashboards to review, verify KYC, and approve/reject pending customer accounts and applications.

### Story 5.1: Branch Admin Approval Queue & Pending Review

User Story: As a Branch Admin, I want to view a pending queue of new customer account registrations and loan requests so that I can evaluate them.

Acceptance Criteria:
• RBAC restricted portal accessible only by users with `ROLE_BRANCH_ADMIN` or `ROLE_LOAN_OFFICER`.
• Data table listing pending requests with applicant name, submission date, KYC status, and request type.

Sub-Tasks Breakdown:

- TASK-05-FE-01: Build Branch Admin Portal layout with sidebar navigation and pending badge counters.

- TASK-05-FE-02: Implement Admin Pending Requests Data Table with sorting, search, and action menus.

- TASK-05-BE-01: Implement RBAC Spring Security rules for `/api/v1/admin/**` endpoints.

- TASK-05-BE-02: Create Admin Queue Service fetching pending approvals across accounts and loans.

### Story 5.2: Decision Processing, Remarks & Audit Logging

User Story: As a Branch Admin, I want to review applicant KYC documents, enter reviewer remarks, and execute Approve or Reject actions.

Acceptance Criteria:
• Modal displaying customer KYC details and simulated documents.
• Mandatory remarks field upon rejection.
• Confirmation modal before state change.
• Immutable audit log entry recorded with Admin User ID, timestamp, prior state, new state, and remarks.

Sub-Tasks Breakdown:

- TASK-05-FE-03: Build Applicant Review modal with KYC document preview and approval/rejection decision form.

- TASK-05-BE-03: Develop State Machine Approval Processor (`PUT /api/v1/admin/approvals/{id}`).

- TASK-05-BE-04: Implement immutable Admin Action Audit Logging service into `admin_audit_logs` table.

# 4. Sprint 2 Backlog: Simulated Transfers, Schedules, Loans & AI (Days 8–14)

## EPIC-06: Simulated Fund Transfers (Own, Other Bank, Mock UPI) (BNK-FR-03)

Epic Description: Build the multi-rail simulated fund transfer wizard covering transfers between own accounts, transfers to registered beneficiaries, and instant mock UPI transfers with simulated OTP verification.

### Story 6.1: Multi-Rail Transfer Initiation Wizard

User Story: As a customer, I want to select a transfer type (Own Account, Other Bank, or Mock UPI), specify source and destination, and input amount with remarks.

Acceptance Criteria:
• 3-Step Wizard: 1. Select Type & Accounts -> 2. Enter Amount & Details -> 3. Review & Confirm.
• Dynamic balance validation: Transfer amount cannot exceed available balance.
• Limits validation: Warn or block if amount exceeds per-transaction or daily limit.
• Remark/purpose dropdown and optional custom text note.

Sub-Tasks Breakdown:

- TASK-06-FE-01: Create 3-step Transfer Stepper Component with live balance indicators and input masks.

- TASK-06-FE-02: Implement Beneficiary Selector dropdown with search-by-name/account and UPI VPA inputs.

- TASK-06-BE-01: Implement Transfer Validation Service (balance checks, active status, daily limits).

- TASK-06-BE-02: Build Transfer Preparation & Quote API (`POST /api/v1/transfers/prepare`).

### Story 6.2: Simulated OTP Verification, Ledger Execution & Receipt

User Story: As a customer, I want to confirm my transfer via simulated OTP, execute the transfer immediately, and view/download a digital transaction receipt.

Acceptance Criteria:
• OTP modal with auto-populated test OTP for simulation convenience.
• Atomic database ledger update: Source account debited, destination account credited (or mock external ledger recorded).
• Real-time balance update on UI upon success.
• Success screen with generated Reference Number (e.g., `TXN-SIM-2026-98124`), date/time, and 'Download Receipt' button.

Sub-Tasks Breakdown:

- TASK-06-FE-03: Create Transfer Confirmation & OTP dialog with countdown and simulated bypass hint.

- TASK-06-FE-04: Build Transfer Success Receipt component with print and PDF export options.

- TASK-06-BE-03: Implement Transactional Transfer Execution Engine (`@Transactional` with Pessimistic Locking on accounts).

- TASK-06-BE-04: Implement Mock UPI payment simulator with probabilistic success/timeout response simulator.

## EPIC-07: Scheduled & Recurring Transfer Engine (BNK-FR-04)

Epic Description: Enable customers to schedule future-dated one-time transfers or establish recurring standing instructions (Daily, Weekly, Monthly) with automated execution simulation.

### Story 7.1: Schedule Future & Recurring Transfer Creation

User Story: As a customer, I want to set a transfer for a specific future date or configure recurring installments so that bills/rent are paid automatically.

Acceptance Criteria:
• Schedule option in transfer form: 'Pay Now', 'Pay Later (One-time)', 'Recurring (Standing Instruction)'.
• Recurrence options: Frequency (Daily, Weekly, Monthly), Start Date, End Date (or Number of Installments).
• Validation prevents past dates or end dates preceding start dates.

Sub-Tasks Breakdown:

- TASK-07-FE-01: Extend Transfer Wizard with Date-Time Picker and Recurring Schedule cadence controls.

- TASK-07-FE-02: Create Schedule Summary & Confirmation review card.

- TASK-07-BE-01: Create Scheduled Transfer persistence entity and repository (`scheduled_transfers`).

- TASK-07-BE-02: Implement Scheduled Transfer Creation API (`POST /api/v1/schedules`).

### Story 7.2: Scheduled Transfers Management & Background Execution

User Story: As a customer, I want to view, pause, or cancel my scheduled transfers, and as a system, execute due transfers automatically.

Acceptance Criteria:
• Scheduled Transfers dashboard tab displaying Active, Paused, and Completed schedules.
• Action to cancel or edit upcoming occurrences.
• Background cron job identifies due schedules, verifies balance, executes transfer, and logs execution status.

Sub-Tasks Breakdown:

- TASK-07-FE-03: Build Scheduled Transfers Management UI with status chips and Cancel/Pause actions.

- TASK-07-BE-03: Implement Spring `@Scheduled` Cron Execution Worker processing due schedules.

- TASK-07-BE-04: Implement Schedule Cancellation & Status Update REST API (`DELETE /api/v1/schedules/{id}`).

## EPIC-08: Loan Application, Eligibility & EMI Calculator (BNK-FR-06)

Epic Description: Implement interactive EMI calculator with loan simulation sliders, loan application submission workflow, document upload simulation, and customer loan status tracking.

### Story 8.1: Interactive Loan EMI Calculator

User Story: As a customer, I want to adjust loan amount, interest rate, and tenure sliders to calculate monthly EMI, total interest, and amortization breakdown.

Acceptance Criteria:
• Dynamic sliders for Loan Amount ($1,000 to $500,000), Tenure (6 to 360 months), and Interest Rate (5% to 20%).
• Real-time recalculation of Monthly EMI, Total Principal, and Total Interest Payable.
• Visual breakdown chart (Principal vs Interest) and 'Apply for this Loan' CTA button pre-populating loan form.

Sub-Tasks Breakdown:

- TASK-08-FE-01: Build Interactive EMI Calculator Widget with dual sliders and numeric input sync.

- TASK-08-FE-02: Implement Amortization Breakdown table and Doughnut chart visual component.

- TASK-08-BE-01: Implement Server-Side Loan Calculation Utility API (`POST /api/v1/loans/calculate-emi`).

### Story 8.2: Loan Application Submission & Status Tracking

User Story: As a customer, I want to submit a formal loan application with income details and mock document uploads, and track its approval progress.

Acceptance Criteria:
• Multi-step Loan Application: Personal Info -> Employment & Income Details -> Mock Document Upload -> Review.
• Application generates unique tracking ID (e.g., `LN-2026-4401`).
• Loan status dashboard displays active loans and submitted applications with stages: Submitted -> Under Review -> Approved/Rejected.

Sub-Tasks Breakdown:

- TASK-08-FE-03: Build Multi-step Loan Application Form with drag-and-drop simulated file uploader.

- TASK-08-FE-04: Create Loan Tracking & Active Loans Dashboard with repayment progress bars.

- TASK-08-BE-02: Implement Loan Application Submission API (`POST /api/v1/loans/apply`).

- TASK-08-BE-03: Implement Mock Document Upload handler and metadata storage.

## EPIC-09: Simulated AI Insights & Risk Assessment (BNK-AI-01 to 05)

Epic Description: Integrate simulated AI advisory capabilities including transaction fraud risk indicators, spending categorization, loan pre-assessment badges, and read-only banking assistant responses.

### Story 9.1: Real-time Transaction Fraud Risk Indicator

User Story: As a system/customer, I want transactions evaluated for simulated fraud risk (Low, Medium, High) so that suspicious transfers require elevated verification.

Acceptance Criteria:
• Rule-based simulated AI risk engine evaluates amount thresholds, unusual hours, and new beneficiaries.
• Returns risk score and risk level (Low, Medium, High).
• High risk triggers mandatory secondary verification warning banner.

Sub-Tasks Breakdown:

- TASK-09-FE-01: Create Fraud Risk Indicator badges and warning alert components on transfer confirmation.

- TASK-09-BE-01: Implement Simulated Fraud Risk Evaluation Service (`POST /api/v1/ai/risk-assessment`).

### Story 9.2: Spending Categorization & Monthly Insights

User Story: As a customer, I want my transactions automatically categorized (e.g., Groceries, Utilities, Entertainment) with monthly spending explanations.

Acceptance Criteria:
• Automatic category assignment based on merchant/remark keywords.
• Dashboard displays monthly spending category breakdown pie chart with conversational AI summary paragraph.

Sub-Tasks Breakdown:

- TASK-09-FE-02: Build Monthly Spending Insights widget with category donut chart and AI narrative card.

- TASK-09-BE-02: Implement AI Spending Categorization & Summary Generator API (`GET /api/v1/ai/spending-insights`).

# 5. Comprehensive Task Master Reference (For Jira Import)

Use the following master matrix to copy and paste directly into Jira issue creation screens or bulk CSV import tools. Every sub-task has clear engineering role ownership, estimated story points, PRD traceability, and sprint assignment.

| Issue Key | Sprint | Issue Type | Summary / Title | Role / Stack | Est. Points |
| --- | --- | --- | --- | --- | --- |
| EPIC-01 | Sprint 1 | Epic | Security, Authentication & Session Inactivity | Full Stack | 13 |
| STORY-01.1 | Sprint 1 | Story | Virtual Keyboard & Secure Customer Login | Full Stack | 8 |
| TASK-01-FE-01 | Sprint 1 | Sub-task | Build accessible, scrambled Virtual Keyboard React component | Frontend (React) | 3 |
| TASK-01-FE-02 | Sprint 1 | Sub-task | Create Login page UI with form validation & eye toggle | Frontend (React) | 2 |
| TASK-01-BE-01 | Sprint 1 | Sub-task | Implement Spring Security JWT auth with BCrypt hashing | Backend (Spring) | 3 |
| TASK-01-BE-02 | Sprint 1 | Sub-task | Configure Rate Limiting & failed login lockout mechanisms | Backend (Spring) | 2 |
| STORY-01.2 | Sprint 1 | Story | Session Inactivity Timer & Warning Dialog | Full Stack | 5 |
| TASK-01-FE-03 | Sprint 1 | Sub-task | Implement global Inactivity Timer hook tracking DOM activity | Frontend (React) | 2 |
| TASK-01-FE-04 | Sprint 1 | Sub-task | Create Timeout Warning Modal with 60s countdown progress bar | Frontend (React) | 2 |
| TASK-01-BE-03 | Sprint 1 | Sub-task | Implement Token Refresh & Server-Side Session Invalidation | Backend (Spring) | 2 |
| TASK-01-BE-04 | Sprint 1 | Sub-task | Add audit log event capture for session timeouts and logouts | Backend (Spring) | 1 |
| EPIC-02 | Sprint 1 | Epic | Customer Account Management & Transaction Ledger | Full Stack | 13 |
| STORY-02.1 | Sprint 1 | Story | Account Summary & Overview Dashboard | Full Stack | 5 |
| TASK-02-FE-01 | Sprint 1 | Sub-task | Create responsive Account Summary card widgets with balance toggle | Frontend (React) | 3 |
| TASK-02-FE-02 | Sprint 1 | Sub-task | Implement Dashboard Layout with Quick Action shortcuts | Frontend (React) | 2 |
| TASK-02-BE-01 | Sprint 1 | Sub-task | Develop Account Query Service & REST Controller | Backend (Spring) | 3 |
| TASK-02-BE-02 | Sprint 1 | Sub-task | Write Flyway migrations for accounts schema | Backend (Spring) | 2 |
| STORY-02.2 | Sprint 1 | Story | Transaction History & Filterable Ledger | Full Stack | 8 |
| TASK-02-FE-03 | Sprint 1 | Sub-task | Build Paginated Transaction Data Grid with filters & drawer | Frontend (React) | 3 |
| TASK-02-FE-04 | Sprint 1 | Sub-task | Implement Transaction Category badges and Debit/Credit styling | Frontend (React) | 2 |
| TASK-02-BE-03 | Sprint 1 | Sub-task | Create Paginated Transaction Search API with JPA Specifications | Backend (Spring) | 3 |
| TASK-02-BE-04 | Sprint 1 | Sub-task | Seed realistic simulated transaction dataset via Flyway | Backend (Spring) | 2 |
| EPIC-03 | Sprint 1 | Epic | Beneficiary Onboarding & Activation Management | Full Stack | 13 |
| STORY-03.1 | Sprint 1 | Story | Add Beneficiary Form & Multi-Rail Validation | Full Stack | 8 |
| TASK-03-FE-01 | Sprint 1 | Sub-task | Create Multi-Tab Add Beneficiary wizard with dynamic validation | Frontend (React) | 3 |
| TASK-03-FE-02 | Sprint 1 | Sub-task | Implement IFSC Bank/Branch mock lookup auto-filler component | Frontend (React) | 2 |
| TASK-03-BE-01 | Sprint 1 | Sub-task | Develop Beneficiary Management Service & REST APIs | Backend (Spring) | 3 |
| TASK-03-BE-02 | Sprint 1 | Sub-task | Implement IFSC and UPI VPA validation logic & duplicate checks | Backend (Spring) | 2 |
| STORY-03.2 | Sprint 1 | Story | Beneficiary Activation & Cooling-Off Period Workflow | Full Stack | 5 |
| TASK-03-FE-03 | Sprint 1 | Sub-task | Build Beneficiary List view with status badges & cooldown timer | Frontend (React) | 2 |
| TASK-03-FE-04 | Sprint 1 | Sub-task | Implement OTP Verification Dialog with resend timer | Frontend (React) | 2 |
| TASK-03-BE-03 | Sprint 1 | Sub-task | Implement Simulated OTP Generation and Verification Service | Backend (Spring) | 2 |
| TASK-03-BE-04 | Sprint 1 | Sub-task | Create Beneficiary Activation Lifecycle Manager | Backend (Spring) | 2 |
| EPIC-04 | Sprint 1 | Epic | Account Statement Generation & Export | Full Stack | 8 |
| STORY-04.1 | Sprint 1 | Story | Statement Customization & On-Screen Viewer | Full Stack | 4 |
| TASK-04-FE-01 | Sprint 1 | Sub-task | Build Statement Generator UI form with date presets & pickers | Frontend (React) | 2 |
| TASK-04-FE-02 | Sprint 1 | Sub-task | Create responsive on-screen Statement Preview component | Frontend (React) | 2 |
| TASK-04-BE-01 | Sprint 1 | Sub-task | Implement Statement Query & Calculation Service | Backend (Spring) | 2 |
| STORY-04.2 | Sprint 1 | Story | Statement PDF & CSV Download Service | Full Stack | 4 |
| TASK-04-FE-03 | Sprint 1 | Sub-task | Implement PDF/CSV direct blob download triggers | Frontend (React) | 1 |
| TASK-04-BE-02 | Sprint 1 | Sub-task | Build high-performance PDF Generator using OpenPDF/iText | Backend (Spring) | 3 |
| TASK-04-BE-03 | Sprint 1 | Sub-task | Implement streaming CSV exporter for transactions | Backend (Spring) | 2 |
| EPIC-05 | Sprint 1 | Epic | Branch Admin Account & Loan Approval Workflow | Full Stack | 13 |
| STORY-05.1 | Sprint 1 | Story | Branch Admin Approval Queue & Pending Review | Full Stack | 5 |
| TASK-05-FE-01 | Sprint 1 | Sub-task | Build Branch Admin Portal layout with sidebar navigation | Frontend (React) | 2 |
| TASK-05-FE-02 | Sprint 1 | Sub-task | Implement Admin Pending Requests Data Table with search/sort | Frontend (React) | 2 |
| TASK-05-BE-01 | Sprint 1 | Sub-task | Implement RBAC Spring Security rules for /admin/** endpoints | Backend (Spring) | 2 |
| TASK-05-BE-02 | Sprint 1 | Sub-task | Create Admin Queue Service fetching pending approvals | Backend (Spring) | 2 |
| STORY-05.2 | Sprint 1 | Story | Decision Processing, Remarks & Audit Logging | Full Stack | 8 |
| TASK-05-FE-03 | Sprint 1 | Sub-task | Build Applicant Review modal with KYC document preview & form | Frontend (React) | 3 |
| TASK-05-BE-03 | Sprint 1 | Sub-task | Develop State Machine Approval Processor for Accounts/Loans | Backend (Spring) | 3 |
| TASK-05-BE-04 | Sprint 1 | Sub-task | Implement immutable Admin Action Audit Logging service | Backend (Spring) | 2 |
| EPIC-06 | Sprint 2 | Epic | Simulated Fund Transfers (Own, Other, UPI) | Full Stack | 21 |
| STORY-06.1 | Sprint 2 | Story | Multi-Rail Transfer Initiation Wizard | Full Stack | 8 |
| TASK-06-FE-01 | Sprint 2 | Sub-task | Create 3-step Transfer Stepper Component with balance indicator | Frontend (React) | 3 |
| TASK-06-FE-02 | Sprint 2 | Sub-task | Implement Beneficiary Selector with autocomplete and UPI VPA | Frontend (React) | 3 |
| TASK-06-BE-01 | Sprint 2 | Sub-task | Implement Transfer Validation Service (limits, balance, status) | Backend (Spring) | 3 |
| TASK-06-BE-02 | Sprint 2 | Sub-task | Build Transfer Preparation & Fee/Quote API | Backend (Spring) | 2 |
| STORY-06.2 | Sprint 2 | Story | Simulated OTP Verification, Execution & Receipt | Full Stack | 13 |
| TASK-06-FE-03 | Sprint 2 | Sub-task | Create Transfer Confirmation & OTP dialog with mock bypass | Frontend (React) | 3 |
| TASK-06-FE-04 | Sprint 2 | Sub-task | Build Transfer Success Receipt component with PDF export | Frontend (React) | 3 |
| TASK-06-BE-03 | Sprint 2 | Sub-task | Implement Transactional Transfer Engine with Pessimistic Locking | Backend (Spring) | 5 |
| TASK-06-BE-04 | Sprint 2 | Sub-task | Implement Mock UPI payment simulator with probabilistic outcomes | Backend (Spring) | 3 |
| EPIC-07 | Sprint 2 | Epic | Scheduled & Recurring Transfer Engine | Full Stack | 13 |
| STORY-07.1 | Sprint 2 | Story | Schedule Future & Recurring Transfer Creation | Full Stack | 5 |
| TASK-07-FE-01 | Sprint 2 | Sub-task | Extend Transfer Wizard with Date-Time Picker & Cadence controls | Frontend (React) | 2 |
| TASK-07-FE-02 | Sprint 2 | Sub-task | Create Schedule Summary & Confirmation review card | Frontend (React) | 2 |
| TASK-07-BE-01 | Sprint 2 | Sub-task | Create Scheduled Transfer entity and repository schema | Backend (Spring) | 2 |
| TASK-07-BE-02 | Sprint 2 | Sub-task | Implement Scheduled Transfer Creation API | Backend (Spring) | 2 |
| STORY-07.2 | Sprint 2 | Story | Scheduled Transfers Management & Background Execution | Full Stack | 8 |
| TASK-07-FE-03 | Sprint 2 | Sub-task | Build Scheduled Transfers Management UI with Cancel/Pause actions | Frontend (React) | 3 |
| TASK-07-BE-03 | Sprint 2 | Sub-task | Implement Spring @Scheduled Cron Execution Worker | Backend (Spring) | 3 |
| TASK-07-BE-04 | Sprint 2 | Sub-task | Implement Schedule Cancellation & Status Update REST API | Backend (Spring) | 2 |
| EPIC-08 | Sprint 2 | Epic | Loan Application, Eligibility & EMI Calculator | Full Stack | 18 |
| STORY-08.1 | Sprint 2 | Story | Interactive Loan EMI Calculator | Full Stack | 8 |
| TASK-08-FE-01 | Sprint 2 | Sub-task | Build Interactive EMI Calculator Widget with sliders & sync | Frontend (React) | 3 |
| TASK-08-FE-02 | Sprint 2 | Sub-task | Implement Amortization Breakdown table & Doughnut chart | Frontend (React) | 3 |
| TASK-08-BE-01 | Sprint 2 | Sub-task | Implement Server-Side Loan Calculation Utility API | Backend (Spring) | 2 |
| STORY-08.2 | Sprint 2 | Story | Loan Application Submission & Status Tracking | Full Stack | 10 |
| TASK-08-FE-03 | Sprint 2 | Sub-task | Build Multi-step Loan Application Form with file uploader | Frontend (React) | 3 |
| TASK-08-FE-04 | Sprint 2 | Sub-task | Create Loan Tracking & Active Loans Dashboard | Frontend (React) | 3 |
| TASK-08-BE-02 | Sprint 2 | Sub-task | Implement Loan Application Submission API | Backend (Spring) | 3 |
| TASK-08-BE-03 | Sprint 2 | Sub-task | Implement Mock Document Upload handler and metadata storage | Backend (Spring) | 2 |
| EPIC-09 | Sprint 2 | Epic | Simulated AI Insights & Risk Assessment | Full Stack | 13 |
| STORY-09.1 | Sprint 2 | Story | Real-time Transaction Fraud Risk Indicator | Full Stack | 5 |
| TASK-09-FE-01 | Sprint 2 | Sub-task | Create Fraud Risk Indicator badges & warning alert components | Frontend (React) | 2 |
| TASK-09-BE-01 | Sprint 2 | Sub-task | Implement Simulated Fraud Risk Evaluation Service | Backend (Spring) | 3 |
| STORY-09.2 | Sprint 2 | Story | Spending Categorization & Monthly Insights | Full Stack | 8 |
| TASK-09-FE-02 | Sprint 2 | Sub-task | Build Monthly Spending Insights widget with donut chart | Frontend (React) | 3 |
| TASK-09-BE-02 | Sprint 2 | Sub-task | Implement AI Spending Categorization & Summary Generator API | Backend (Spring) | 3 |

Table 3: Master JIRA Backlog Matrix (Epics, Stories, and Sub-Tasks)